## How to use
Challenge assumptions — team workbook
lateralworks · generic template · pre-work for a challenge workshop
Purpose | Collect the assumptions baked into your program before the workshop, then challenge them live as a team. The test for every assumption: if we relaxed it, would the outcome we want (schedule, cost, scope) improve?
The flow | Area of focus → Assumptions → Select → Why? → Do / Cut, or Challenge → Ideas → Act. Surface assumptions, dot-rank them, interrogate the high-leverage ones, and turn the challenged ones into ideas and actions.
Four ways to phrase an assumption
It is essential that… | It is essential that the lead customer actively engages.
… dominates our thinking | Schedule > quality dominates our thinking.
We must avoid… | We must avoid multiple projects at the same time.
We must stay within … boundary | We must stay within current resource constraints — we can't hire.
The leverage test
GOOD — has leverage | Assumption: "We must have xyz performance at first release." → If relaxed, a whole test matrix drops out and the schedule pulls in.
BAD — no leverage | Assumption: "Company X is the first customer." → Relaxing it changes nothing you can act on. Park it.
How to read the register
Category | One of the four phrasings above.
Why we believe this | The reasons behind the assumption. Ask: are the reasons still valid?
What changes if relaxed | The specific move you would make if you stopped believing the assumption.
Leverage | Pre-rating to seed the ranking: High / Med-High / Med / Low.
Workshop dots | Leave blank — for sticky-dot ranking in the room. Most dots get challenged first.
Disposition | Leave blank — filled live in the workshop: Challenge / Keep / Do / Cut.
The Risks register tab | Some inputs are events that could hit the program rather than beliefs about how it must run. Keep those on the Risks tab and treat them separately: is this a real risk, and what can we do to reduce the impact or lower the likelihood?
Cells to fill in | Cells with the light-yellow fill are yours to complete. Example rows show the expected format — replace them with your own program's assumptions.
lateralworks · template — adapt freely for your own challenge workshop

## Assumptions register
Assumptions register — candidates for challenge
lateralworks · generic template · consolidated team inputs, collected anonymously before the workshop
ID | Category | Assumption | Why we believe this | What changes if we relax it | Pull-in mechanism (what it attacks) | Leverage | Owner / area | Workshop dots | Disposition
A1 | It is essential that… | It is essential that the first release meets the full published specification across all features and modes. | Broad addressability — one product serves every customer. | Qualify the subset the lead customer actually needs first; add the rest in a fast follower. | Shrinks the test and validation matrix. | High | Design / product
A2 | It is essential that… | It is essential that the lead customer actively engages in the program. | Sign-off, feedback and requirement clarity all depend on it. | Secure a named engagement owner and a fixed feedback cadence. | Enabler — removes feedback latency on the critical path. | High | Commercial
B1 | … dominates our thinking | First-time-right technical completeness dominates our thinking, over schedule. | Engineering culture; reputational stakes. | Adopt "sufficient for first qualification" inside a defined quality floor. | Removes scope and perfection churn. | High | Leadership
B2 | … dominates our thinking | Risk avoidance dominates our thinking. | A failed build or iteration genuinely adds time. | Accept bounded, recoverable risk where a failure would not hit the critical path. | Compresses the verify-everything serial chain. | Med-High | Program
C1 | We must avoid… | We must avoid starting any long-lead activity before design freeze. | Rework risk if the design changes after the start. | Pre-stage long-lead items at your own risk; buy back calendar time. | Compresses the serial design-to-build handoff. | High | Program
C2 | We must avoid… | We must avoid developing the test program in parallel with the redesign. | The test program depends on the final design; parallel work could be wasted. | Build the test program concurrently against the stable 90%. | Removes a serial tail after the build arrives. | Med-High | Test lead
D1 | We must stay within … boundary | We must stay within current engineering headcount — we cannot hire or borrow resources. | Budget, runway and hiring lead time. | Targeted contract or loaned expertise on the bottleneck skills only. | Breaks the owner-concentration bottleneck. | High | Leadership
D2 | We must stay within … boundary | We must stay within the existing serial design → build → test sequence. | Standard process; it is how we have always run. | Authorize concurrent engineering across the boundary; overlap phases. | Overlaps phases currently run end-to-end. | Med-High | Program
Example rows A1–D2 show the expected format — replace with your own. Yellow cells are yours to fill in.

## Risks register
Risks register — inputs better treated as risks than assumptions
lateralworks · generic template · challenged separately: is it real, and how do we reduce impact or likelihood?
ID | Risk | Why it is credible / trigger | Impact if it hits | Related assumptions | Risk-reduction ideas / workshop question | Workshop dots | Disposition
R1 | The lead customer does not accept the reduced first release. | The minimum viable product has not been formally agreed. | Rework and requalification against different requirements. | A1, A2 | Present the minimum viable product to the customer now and obtain written acceptance.
R2 | Unclear ownership in key areas lets tasks and decisions stall. | Ownership has not been made explicit across all program areas. | Latency and dropped hand-offs, on and off the critical path. | D1 | Name a single owner per area before the workshop and make ownership visible.
Kept separate from the assumptions register: these are events that could hit the program, not beliefs about how it must run.

## Category summary
Category summary
Category | High | Med-High | Med | Low | Total
It is essential that… | 2 | 0 | 0 | 0 | 2
… dominates our thinking | 1 | 1 | 0 | 0 | 2
We must avoid… | 1 | 1 | 0 | 0 | 2
We must stay within … boundary | 1 | 1 | 0 | 0 | 2
Total | 5 | 3 | 0 | 0 | 8
Pre-ratings seed the dot-ranking; they are not the verdict. The room decides.