## Refresh Basics
Refresh Basics
1. Update - 30 minutes or less
1.1 | All task owners - All task owners come prepared with their completed PreFresh Lookahead Reports - If a task owner can’t attend, they are responsible to get the PM the updates in advance via a completed PreFresh Lookahead Report - If a task owner can’t attend and can’t complete the Lookahead Report in advance, they are responsible for appointing a stand-in to attend in their absence
1.2 | Start on time, end of time - never cancel, always run the update meeting
1.3 | Use the minimal update interface to speed up the Update (hide the Start/Finish dates)
1.4 | Update quickly - minimal content discussion (<5 seconds/task)
1.5 | Mark tasks that need further discussion, record notes as needed on the task
1.6 | When completed, scroll through each target and review what changed based on the Update
2. Pull-in - 30 minutes or less
2.1 | Using the Inspector, select the first target and look at the Critical Path. Turn the baseline on to show where the tasks were at the start of the update. This will show the changes caused by the Update, specifically the cause of the slip/pull-in. Discuss the cause of the slip or pull-in.
2.2 | Walk down the path, starting with the first task and, with the team, ask if anything can be done to pull-in: can we do tasks concurrently? can we eliminate tasks?, can tasks be done faster? This is where task owners must engage to brainstorm how to accelerate their schedule.
2.3 | Make the changes live as these changes could change the critical path to that target, then re-filter on the Critical Path to the target. Repeat until you recover (at least) any time lost. Keep going until you can’t pull-in any more.
2.4 | Assign one team member to take notes. If changes can’t be made live, have them record the action that needs to happen in order to execute the pull-in. Make sure to close all action items before the next Refresh meeting. They should be on this list for no more than 7 days.
2.5 | Repeat 2.1-2.4 for each target in the project.
2.6 | Run the Wigglechart and review each target with the team. Record, the reason for the schedule change that week at bottom of chart.

## Project Assessment
Refresh Planning Assessment |  |  | A "0" score indicates it is not happening
|  |  | Team Self Assessment |  | External Assessment
# | Area | Best Practice | Score (0-5) | Comment | Score (0-5) | Comment
1 | Timing | Meeting takes place at least once a week, at the same time
2 | Timing | Meeting starts and finishes on time, with all owners present on time and present for full duration of meeting
3 | Participation | All task owners (or manager responsible for clusters of tasks) are present, either in person or online. If in the office, they are present in person.
4 | Participation | Each owner comes to the meeting prepared with their updates and actively participates in the meeting
5 | Participation | If an owner is not able to attend, they have either provided their updates to the PM in advance (either in person or a completed PreFresh report) or they have a knowledgeable person stand-in for them
6 | Pre-Refresh | The Pre-Fresh LAR is run the day prior to the Refresh Meeting and distributed to all owners. All owners understand LAR report contents and how to use it through the week.
7 | Update | Automatic Updates: Completed PreFresh reports are automatically loaded prior to team meeting. Assumes owners have been trained and understand how to complete LAR without errors.
8 | Update | Manual Updates: Are made to the schedule quickly (<5 seconds per response), with minimal discussion. The PM controls the discussion. The team members are present or online.
9 | Update | PM asks the update questions (Has it started?, Has it finished? Number of days remaining?) and waits for a response
10 | What Changed? | Immediately after Updates are entered, each target's change is reviewed to assess the impact of the update. Did the schedule to each target push out or pull-in?
For each Target, doing the following (11-18):
11 | Pull-in | 1st Critical Path: The critical path is walked, including the change from the previous baseline to identify the cause of the pull-in or push-out, and is discussed.
12 | Pull-in | 1st Critical Path: While walking the critical path, pull-in opportunities are identified/discussed.
13 | Pull-in | 1st Critical Path: Pull-ins are implemented in the schedule (live). The impact of the pull-in is assessed. Owners who have to execute the pull-in have confirmed their understanding. Any actions needed outside of the schedule have been recorded.
14 | Pull-in | 1st Critical Path: Any pull-ins that CANNOT be immediately implemented in the schedule are put into a weekly Pull-in action tracking log, with an owner. Each pull-in action must be completed before the next refresh.
15 | Pull-in | 1st Critical Path: If the project is on schedule, or early, the team tries to find additional ways to accelerate the critical path and implements these live into the schedule.
16 | Pull-in | Critical Paths 2-3: Peel back and display the 2nd and 3rd critical paths, including the change from the previous baseline which identifies the cause of the pull-in or push-out
17 | Pull-in | Critical Paths 2-3: Items 10-14 above are repeated for critical paths 2-3
19 | Post-Refresh | (Advanced) Micro schedules are rolled-up/down If not time consuming, can be done after step 9
18 | Pull-in | Run Wigglechart and review results of the Update and Pull-in on each target milestone. Enter reason for change in direction for each target milestone.
20 | Post-Refresh | Run Schedule Analyzer. Get score of >90 and fix reported errors.
21 | Post-Refresh | Post-Fresh LAR is run immediately after the Refresh Meeting and distributed to all owners
Post Refresh Analysis (with a subset of the team):
22 | Analysis | The Critical Path Analysis bar chart is generated, analyzed and macro-pull-in opportunities explored to get back to target (causes, impacts, possible solutions to shorten each path)
23 | Follow-up | Pull-in actions that were not able to be implemented live in the Refresh Meeting are followed up on to ensure they get done
24 | Follow-up | Owners on the top ~3 critical paths are identified and this is communicated to them on a weekly basis
25 | Reporting | Project Status report(s) are distributed to team members and executive management
General: | Y/N
Are Updates collected through a group meeting (manually)?
Are Updates collected individually (manually)?
Are Updates collected electronically collected and then automatically input through LAR import?
Are Updates and Pull-in done in same meeting with (core) team present (if NO, assumes in 2 meetings)
Project Name:
Program Manager:
Refresh Date:
Refresh Time: