## Project Scope
Quartz memory-acceleration card | PS
Goal
Ship the company's Quartz card via the systems integrator to hyperscaler production by end Q2 2028 with 5-8x insert speedup.
Success Criteria
Production-ready card entered the market by end Q2 2028 (conservative plan: end Q3 2028).
Card delivered 5-8x insert and 6-8x GET throughput over baseline with flush enabled.
Card supported any key size and software-based scan.
the systems integrator signed as OEM channel on agreed pricing and margins.
One or more hyperscalers committed to volume through the systems integrator.
Alpha customers secured inside and outside the systems integrator.
Hardware COGS held at about $1,300 per card at 5K units per year.
the company average revenue reached the $3,600 per-card plan (hardware, support and SW, without memory).
Order pipeline supported the 2028 plan of 780 cards and $2.2M revenue.
Installed base exceeded 12K cards by 2031 (slide 5).
Assumptions
Dates follow the aggressive plan; the conservative plan slips HW design, samples and production one quarter.
the company budget is secured through December 2026; 2027 continuity is required to proceed past M2.
the systems integrator acts as OEM channel, motivated by a margin that offsets ~$900 gross profit loss per server.
Customer value is $8,400 per card over 3 years less $700 for a 32 GB persistent-memory module: $7,700 net (2026 draft).
Card value splits customer / the systems integrator / the company at 30% / 30% / 40% (2026 draft).
Hardware COGS is ~$1,300 per card: $900 FPGA at 5K units per year plus ~$400 PCB.
Target customers are two Tier 1 hyperscalers first, then Tier 2 enterprise (HP, Dell).
Revenue combines hardware sales with recurring support and SW licenses.
HW design hiring triggers on M4 (aggressive plan) or M5 (conservative plan).
The card enters the datacenter market as a COTS solution and validates application and channel for DRAM+.
Risks
Hyperscaler volume agreement slips; large companies move slowly (High).
Flush performance pulls insert throughput below the 5-8x target.
GET performance remains TBD weeks before POC close and misses the 2-3x target.
Team transition during Q4 2026 delays POC delivery to the systems integrator.
Requested hyperscaler use case falls outside workloads the company already evaluated.
2027 budget is not secured before December 2026 funding ends.
No HW design partner is found at the target PCB price point.
the systems integrator declines the eval kit purchase if M1 results underwhelm.
Pricing and margin terms fail to compensate the systems integrator for lost server sales.
Value model remains a 2026 draft that no hyperscaler has validated.
Speaker notes on the economics slide carry a different model (the company 30%, the systems integrator 20%, customer 20% plus 30% unpriced, $2,150 hardware ASP, Gen1 FPGA bill of materials of $2,600 at negative hardware margin, $4,300 revenue per card over five years) than the slide itself; reconcile before the value model is finalized at M1.
Slide 1 dates product maturity and market expansion (Q4 2027) before market entry (Q2 2028); reconcile the sequence.

## Major Milestones
MM
M# | Summary Task | Milestone Name | Doneness Criteria | Subtasks | Assumptions | Risks
M1 | Validate POC performance and quantify business value | POC performance validated | - Insert throughput reached 5-8x over the baseline configuration. - GET throughput reached 2-3x over baseline. - POC scope held: no flush, no scan, keys of 64 B or less. - Final performance and per-card business value quantified; the 2026 draft value model finalized. | - Measure insert throughput across batch sizes (4 to 32 KV pairs) and thread counts - Measure GET throughput against the 2-3x target - Compare all results against the baseline-defaults configuration - Finalize the per-card value-sale economics model - Publish the final performance and business value summary | - Target date: mid Q4 2026 (both plans) - POC scope excludes flush and scan; keys of 64 B or less - Results to date: up to 6x at batch of 4 KV pairs, up to 10x at batch of 32 - Budget covers POC work through December 2026 | - Rating: Med - Read performance still TBD; GET misses 2-3x - Insert gain falls below 5x at small batch sizes - Draft value model ($7,700 net 3-year customer value) fails review - Speaker notes value model (the company 30% / the systems integrator 20% / customer 20% / 30% unpriced, $2,150 ASP) conflicts with the slide (30 / 30 / 40, $3,600 per card)
M2 | Engage the systems integrator and solicit hyperscaler use cases | Systems integrator engaged and eval kit committed | - the integrator's engineering and business teams engaged on the card. - the systems integrator solicited use cases from one or more hyperscalers. - the systems integrator committed to an eval kit purchase. | - Present final performance and business value to the integrator's engineering and business teams - Define eval kit contents and terms - Support the systems integrator's use case solicitation with hyperscalers - Close the systems integrator's eval kit purchase commitment | - Target date: end Q4 2026 (both plans) - Successful engagement means the systems integrator purchased an eval kit - the systems integrator's OEM margin offsets its lost server sales | - Rating: Mid (depends on M1) - Weak M1 results stall the systems integrator engagement - Hyperscalers give no use case input before year end
M3 | Deliver the POC with flush to integrator engineering | POC delivered to integrator engineering | - the company delivered the POC to the systems integrator's engineering team for evaluation. - Insert held at 5-8x with flush enabled. - GET reached 6-8x over baseline. - Scope held: no scan support, keys of 64 B or less. | - Implement flush support and hold insert throughput at 5-8x - Raise GET throughput from 2-3x to 6-8x - Package POC hardware, software and documentation for evaluation - Hand over the POC and support the systems integrator's evaluation setup - Cover POC ownership through the Q4 2026 team transition | - Target date: mid Q1 2027 (both plans) - Scan support and keys over 64 B stay out of scope - 2027 budget is secured | - Rating: Mid-High - Team transition during Q4 2026 delays delivery - Flush performance pulls insert below 6x - GET gain from 2-3x to 6-8x needs more than one tuning cycle
M4 | Align POC software to the hyperscaler use case | Hyperscaler use-case value demonstrated | - POC software aligned to the hyperscaler's use case. - the company and the systems integrator completed joint engineering validation on that use case. - Bugs fixed and the system tuned for the target workload. - Value demonstrated on the customer's own use case. | - Map the hyperscaler use case to POC capabilities - Align POC software to the use case - Run joint the company-integrator engineering validation - Fix bugs and tune the system on the target workload - Quantify and present use-case value to the systems integrator and the hyperscaler | - Target date: end Q1 2027 (both plans) - Hyperscaler use case input arrived through M2 - Aggressive plan: M4 success triggers HW design hiring | - Rating: Mid - Requested use case falls outside evaluated workloads - Use case needs scan or keys over 64 B before the product card delivers them - Demonstrated value falls short of the value model
M5 | Negotiate pricing and secure hyperscaler volume | Commercial terms and hyperscaler volume agreed | - the company and the systems integrator agreed pricing and margins (beginning Q2 2027). - Card value split agreed across customer, the systems integrator and the company (draft: 30 / 30 / 40). - A hyperscaler agreed to volume through the systems integrator. | - Agree pricing and margins with the systems integrator - Confirm the customer / the systems integrator / the company value split - Open hyperscaler volume discussions as soon as M4 succeeds - Close the hyperscaler volume agreement through the systems integrator | - Target date: end Q2 2027 (both plans); pricing at beginning Q2 2027 - Value split 30 / 30 / 40 customer / the systems integrator / the company (2026 draft) - Conservative plan: volume agreement triggers HW design hiring | - Rating: High (pricing alone Low-Mid) - Large companies move slowly; volume agreement slips - Pricing terms hinge on the M4 outcome - the systems integrator margin fails to offset ~$900 gross profit loss per server
M6 | Design the product card and build engineering samples | Engineering samples delivered | - Engineering samples built and fulfilled. - Insert reached 5-8x and GET 6-8x with flush enabled. - Software-based scan support delivered. - Any key size supported. | - Scope HW design, validation and testing (mid Q2 2027; conservative mid Q3 2027) - Find, vet and sign the HW design partner (end Q2 2027; conservative end Q3 2027) - Hire the HW design team on the trigger milestone - Design the card and develop software-based scan and any-key-size support - Build, validate and fulfill engineering samples | - Target date: end Q1 2028 (conservative: end Q2 2028) - Hardware COGS ~$1,300 per card ($900 FPGA at 5K units per year + ~$400 PCB) - Hiring trigger: M4 (aggressive) or M5 (conservative) | - Rating: Mid - Flush performance pulls insert below 6x - No PCB partner at the target price point - Late hiring trigger compresses the design window
M7 | Ready the card for production and market entry | Production ready for market entry | - Card declared production ready. - HW design optimized for performance and cost. - Marketing, user and support collateral built and reviewed. - Alpha customers secured inside and outside the systems integrator. | - Optimize the HW design for performance and cost - Build and review marketing, user and support collateral - Secure alpha customers inside and outside the systems integrator - Ready production builds and order fulfillment | - Target date: end Q2 2028 (conservative: end Q3 2028) - Plan basis: 780 cards and $2.2M revenue in 2028 - Channel: OEM through the systems integrator; Tier 1 hyperscalers first, Tier 2 enterprise next - Installed base >12K cards by 2031; 7,400 cards and $24M revenue in 2031 per the units and revenue charts | - Rating: not rated in source - Source deck dates product maturity (Q4 2027) before market entry (Q2 2028); reconcile - No alpha customers yet identified outside the systems integrator - Engineering sample slip cascades one quarter